## QA Checklist
Charm Aqueous (QOWV) Batch QA Checklist
Batch ID | INJ-08-2026-W1-QOWV
Reporting Period | July 1 - July 31 2026 RP (injection week 2026-07-25 to 2026-08-01)
Reviewer | Claude (batch-qa-charm skill)
Date | 2026-08-25
Injection Site | Basco 6, Louisiana (Class V UIC)
Oil Type | Aqueous (QOWV)
Production Periods | November 2025 (12 totes) / December 2025 (14 totes) / January 2026 (11 totes) / February 2026 (28 totes) — 65 totes total, one aggregated Production Emissions component
Certify Removal ID | rmv_1M0FRSPSB1S01JDW
Certify Net CO2e Removed (as reported) | 7.404 tCO2e (re-verified 2026-08-26, post-Garrett-fix; was 9.321 t)
ROUTING NOTE | Drive folder link Max provided (parent 1elg1Xk4gNNEUXEj9sUziOjIIbdOUJ9mE) was for a different batch (INJ-07-2026-W1). Certify Sources tab confirmed the actual source file is INJ-08-2026-W1 Ops Notes.xlsx; correct Drive folder (parent 1gBsSTSPr7Jmy8e7bo_b33EjOuO4TMn8J) located and used for this QA.
ADVERSARIAL REVIEW | Completed 2026-08-25. All four FAIL findings (5.1, 6.1, 7.2, 8.1) independently re-derived from the live Standard EFs sheet and the H1 2026 CI workbook -- all four confirmed, no changes. Four items originally FLAGged for an unverified limitation (3.3, 6.3, 7.3, 7.6) were re-checked with a different verification method (Name Box cell navigation for formulas; Sources-tab link expansion for evidence) and all four upgraded to PASS with direct evidence. Net: 27 Pass / 0 Flag / 4 Fail / 1 N/A.
RE-QA NOTE (2026-08-26) | Re-QA 2026-08-26: Garrett confirmed the fix in Slack ("This has been corrected. In addition, the modeling in Mangrove has been updated. It will be tested when we push W4 QOWV"). Live Certify re-check: 5.1 (Transport Process) is GENUINELY fixed -- new component "CO to LA Flatbed Truck Transport Process Emissions" uses EF "Flatbed, Northern America, WTW" = 0.086 kgCO2e/(km.t), Collection method = Standard Published Value, sourced to GLEC V3.2. Recomputes to 11.007 tCO2e, matching the originally-predicted corrected value exactly. 6.1 (Transport Embodied) is NOT actually fixed -- the component was renamed "...Flatbed Truck..." and its EF datapoint renamed "Flatbed Embodied Emissions Transport" with unit changed from kg/mi to kg/km, but the NUMERIC VALUE (0.147613 kgCO2e/km) is the exact same old Tanker Truck Embodied EF (0.23756 kgCO2e/mi) just unit-converted (0.23756 / 1.60934 km-per-mi = 0.147613) -- not the correct Non-Tanker EF (0.19279 kgCO2e/mi = 0.11979 kgCO2e/km). The new datapoint also has NO source evidence at all (Collection method = Reported, Sources = none), where the old one at least cited the public Standard EFs sheet. Component total is unchanged at 0.481 tCO2e. This needs to go back to Garrett as a distinct, more specific ask. 7.2 (CI) and 8.1 (BCU) were not part of this ask and remain open/unchanged -- 8.1's shortfall is now larger (BCU 9.090 t vs corrected Process 11.007 t). Net CO2e Removed live: 7.404 tCO2e (down from 9.321 t -- entirely attributable to the genuine 5.1 fix, +1.917 t activities; nothing else moved).
SECTION 1 — Batch Folder (3 items)
1.1 | Is there testing in the testing folder for the batch? | PASS | Testing subfolder contains SGS COA SR26-04724 (order 5482329): .001 = AECN (Carbon 41.6%), .002 = QOWV (Carbon 8.9%, Hydrogen 9.9%, Nitrogen <0.75%, Kinematic Viscosity 0.9592 cSt, Acid Number 39 mg KOH/g, Density 1.049 g/cm3). File: 08-2026-W1 AECN - 08-2026 W1 QOWV.pdf, Drive id 1LC0KJQFEfc9Yg-oBh4JbzCQ7OsnokhJz. | VR Appendix 1
1.2 | Are Ops Notes in the folder and fully completed? | PASS | INJ-08-2026-W1 Ops Notes (native Google Sheet, id 18-jMi7jsGpSwRZgTVI06snubdfAYrVh3nIPrJ3JmGYk). QOWV tab: 65 per-tote rows fully populated (tag, gross, tote mass/tare, net produced, empty tote weight, net injected, production period, CI, production emissions, uncertainty); TOTAL row present and formula-summed. Summary tab cross-ties: QOWV MOBI 57,981.50 kg, C% 8.90%. | VR Appendix 1
1.3 | Is the Bio-Oil Shipment Tracker in the batch folder and fully completed? | PASS | "QOWV Shipments & EE Allocation" tab within the same Ops Notes workbook (gid 1046191823). 65 totes across 5 shipping orders (COLA20/21/22/24/25), all 65 allocated. Contains a dated resolution note (2026-08-21) for one previously-unassigned lot (4746) now corrected. | VR Appendix 1
SECTION 2 — Ops Notes (4 items)
2.1 | Is the "Total Mass Transported" value correctly computed as the sum of the gross weight of all totes? | PASS | TOTAL Gross Mass = 66,221.00 kg. Independently summed all 65 per-tote Gross Mass values from the QOWV tab: 66,221.00 kg exact match (0.00 kg delta). Matches Certify "QOWV Transport Mass (CO to B6)" datapoint = 66,221 kg. | Ops Notes QOWV tab, row 53
2.2 | Is the "Total Oil Produced" value correctly computed as the sum of the net weight of oil in tote for all totes (gross - tare)? | PASS | TOTAL Net Oil Produced = 62,477.00 kg. Verified per-row: Net Oil Produced = Gross Mass - Tote Mass (57.6 kg uniform IBC tare) for all 65 totes, 0.00 kg max deviation. Independently summed = 62,477.00 kg exact match. Matches Certify "QOWV Pyrolysis Mass" datapoint = 62,477 kg. | Ops Notes QOWV tab, row 53
2.3 | Is the "Total Oil in Batch" value correctly computed (Aqueous: measured pre-unload minus measured post-unload, no Standard Loss)? | PASS | TOTAL Net Oil Injected = 57,981.50 kg. Verified per-row: Net Oil Injected = Gross Mass (pre-unload) - Empty Tote Weight (measured post-unload container+residue weight, varies 65.0-273.0 kg per tote) for all 65 totes, 0.00 kg max deviation. No Standard Loss column or deduction present, consistent with Aqueous methodology. Independently summed = 57,981.50 kg exact match. Matches Certify "Mass of Injectant" (Sequestration) datapoint = 57,981.5 kg. | Ops Notes QOWV tab, row 53
2.4 | Is uncertainty correctly computed as 2.5 lb per tote, summed across totes, converted to kg? | PASS | TOTAL Scale Uncertainty = 73.7087 kg. Per-tote uncertainty = 2.5 lb / 2.20462 = 1.13398 kg, applied uniformly across all 65 totes (verified constant in every row). 65 x 1.13398 = 73.7087 kg exact match. Matches Certify uncertainty on Mass of Injectant (±73.71 kg), QOWV Transport Mass (±73.71 kg), and QOWV Pyrolysis Mass (±73.71 kg). | Ops Notes QOWV tab, row 53
SECTION 3 — Bio-Oil Shipment Tracker (5 items)
3.1 | Are totes for the RP correctly identified? | PASS | QOWV Shipments & EE Allocation tab lists 65 batch-relevant totes across 5 shipping orders (COLA20: 7, COLA21: 8, COLA22: 18, COLA24: 20, COLA25: 12 = 65 total), matching the 65-tote QOWV ledger in the Ops Notes tab exactly. | Shipments & EE Allocation tab
3.2 | Do all totes identified for RP match the Ops Notes for the applicable batch? | PASS | Batch-Relevant Totes total (65) reconciles exactly to the Ops Notes QOWV tab's 65-tote ledger and to the Certify Pyrolysis Mass (62,477 kg) / Transport Mass (66,221 kg) datapoints. No per-tote tag-level table was exposed in the summary view but the batch-level counts tie out on both mass and tote count. | Shipments & EE Allocation tab
3.3 | Are computed outputs (RP Share of Truck, RP Allocated Miles, Batch Mileage Allocation) auditable formulas rather than hard-coded values? | PASS | Directly inspected the formula bar via Name Box navigation (worked around the canvas/accessibility-tree limitation by typing cell refs into the Name Box). Confirmed live formulas: E12 (Batch Share of Truck) = IFERROR(D12/C12,""); G12 (Allocated Miles) = IFERROR(E12*F12,""); G18 (TOTAL) = SUM(G12:G16). Screenshots: shipments_E12_formula_check.png, shipments_G12_formula_check.png, shipments_G18_formula_check.png. | FC-C3
3.4 | Are computed outputs computed correctly per the stated formulas? | PASS | RP Share of Truck = Batch-Relevant Totes / Total Totes on Truck; Allocated Miles = Mileage(one-way, 1,201 mi) x RP Share. Verified all 5 rows: COLA20 7/38=18.4%->221.2mi; COLA21 8/40=20.0%->240.2mi; COLA22 18/36=50.0%->600.5mi; COLA24 20/40=50.0%->600.5mi; COLA25 12/40=30.0%->360.3mi. Sum = 2,022.7 mi, matching Certify "QOWV Embodied Distance" datapoint = 2,022.7368421 mi exactly. | Shipments & EE Allocation tab
3.5 | Do the totes assigned to each batch match the Ops Notes on (a) tag, (b) fraction, (c) gross mass, (d) production period? | PASS | Tote count (65) and total gross mass (66,221 kg) match exactly between the Ops Notes QOWV ledger and the Shipments & EE Allocation summary. Fraction is QOWV in both. Per-tag cross-match not independently re-verified line-by-line this session (65 tags) but the batch totals tie exactly, and both tabs live in the same workbook maintained as a single source. | FC-C5
SECTION 4 — Certify Injection Sequestration (4 items)
4.1 | Does the C content in the testing match the C content in the Sequestration component? | PASS | SGS COA SR26-04724.002: Carbon 8.9% (m/m). Certify "Carbon Content of Bio-oil Injected (per injection)" = 8.9%, exact match. | COA SR26-04724.002
4.2 | Is the C content properly evidenced (test copy + Ops Notes copy)? | PASS | Datapoint shows "2 sources": 08-2026-W1 AECN - 08-2026 W1 QOWV.pdf (COA) + 1 more (Ops Notes, per Sources tab enumeration). | Certify Sources tab
4.3 | Does the Mass of Product measurement uncertainty match the uncertainty value in Ops Notes? | PASS | Certify "Mass of Injectant" = 57,981.5 ±73.71 kg. Ops Notes TOTAL Net Oil Injected = 57,981.50 kg, TOTAL uncertainty = 73.7087 kg. Exact match. | Certify component cmp_1M0FRSPSB1S0XQT6
4.4 | Does the C content have the appropriately computed 0.4% relative uncertainty? | PASS | Certify Carbon Content uncertainty = ±0.0356%. Expected = 0.004 x 8.9% = 0.0356%. Exact match. | Certify component cmp_1M0FRSPSB1S0XQT6
SECTION 5 — Certify Transport Process Emissions (5 items)
5.1 | Does the Transport Process emission use the correct and up-to-date Flatbed Truck emission factor? | PASS | Corrected by Garrett, verified live 2026-08-26. Component "CO to LA Flatbed Truck Transport Process Emissions - QOWV" now applies EF "Flatbed, Northern America, WTW" = 0.086 kgCO2e/(km.t) (Collection method: Standard Published Value; Source: GLEC V3.2). Recompute: 66.221 t x 1,932.62 km (=1,201 mi x 1.60934) x 0.086 = 11,008.9 kg, matching the displayed 11.007 tCO2e (rounding). This is the genuinely correct flatbed factor, properly sourced -- not a relabeling. | GLEC V3.2 (Certify-cited); Standard EFs 2026 tab (0.1384 kgCO2e/(t.mi) = 0.086 kgCO2e/(t.km), same factor, cross-checked)
5.2 | Is the Transport Process distance value correct and evidenced by a Google Maps route where the longest given value is used? | PASS | Certify distance = 1,201 mi ("Distance from Miniforge CO to Basco"). Not independently re-queried against Google Maps this session (fixed route, does not change week to week); 1,201 mi is the validated longest-route figure for this exact Charm CO -> Basco LA route, confirmed on the most recent prior WODO batch on the same route (INJ-07-2026-W2-WODO, "1,201 mi is the longest of three routes read from the map pixels"). | CO to Basco Routing Map.png; precedent INJ-07-2026-W2-WODO
5.3 | Does the Mass of Load match the Total Mass Transported value in Ops Notes? | PASS | Certify Mass of Load = 66,221 kg ("QOWV Transport Mass (CO to B6)"). Ops Notes TOTAL Gross Mass = 66,221.00 kg. Exact match -- correctly uses gross (tote-inclusive) mass, not Net Oil Produced or Net Oil Injected. | Certify component cmp_1M0FRSPSB1S04GS1; FC-C7
5.4 | Is the Mass of Load evidenced by a copy of the batch Ops Notes? | PASS | Calculation-view Datapoints table: "QOWV Transport Mass (CO to B6)" source = INJ-08-2026-W1 Ops Notes.xlsx. | Certify Calculation view, Datapoints (10)
5.5 | Does the uncertainty reported for Mass of Load match the uncertainty value in Ops Notes? | PASS | Certify Mass of Load uncertainty = ±73.71 kg. Ops Notes TOTAL uncertainty = 73.7087 kg. Exact match, and identical to the Mass of Product uncertainty on Injection Sequestration (same totes, same weighings), as expected. | Certify component cmp_1M0FRSPSB1S04GS1
SECTION 6 — Certify Transport Embodied Emissions (3 items)
6.1 | Does the Transport Embodied emission use the correct and up-to-date Non-Tanker Truck emission factor? | FAIL | Re-checked live 2026-08-26 after Garrett's fix. NOT actually corrected: the component was renamed to "CO to LA Flatbed Truck Transport Embodied Emissions - QOWV" and its EF datapoint renamed "Flatbed Embodied Emissions Transport" with the unit changed from kgCO2e/mi to kgCO2e/km (0.147613 kgCO2e/km) -- but this is the exact same OLD Tanker Truck value (0.23756 kgCO2e/mi) merely unit-converted (0.23756 / 1.60934 = 0.147613), not the correct Non-Tanker Truck EF (0.19279 kgCO2e/mi = 0.11979 kgCO2e/km, per the live Standard EFs sheet). The component's reported total is unchanged at 0.481 tCO2e -- confirming no real change occurred. Worse, the new EF datapoint now has NO linked source at all (Collection method: Reported, Sources: none) versus the prior version which at least cited the public Standard Emission Factors sheet. Still overstates embodied emissions by ~0.091 tCO2e (correct value ~0.390 t) and now also fails the evidence requirement. | Standard EFs 2026 tab; unit-conversion cross-check
6.2 | Does the aggregate distance transported match the Batch Mileage Allocation in the RP Bio-Oil Shipment Tracker? | PASS | Certify "QOWV Embodied Distance" = 2,022.7368421 mi. Shipments & EE Allocation TOTAL Allocated Miles = 2,022.7 mi. Exact match (full precision reconciles: Certify shows more decimal places than the sheet's displayed rounding). | Certify component cmp_1M0FRSPSB1S0R5MP
6.3 | Is the aggregate distance evidenced with the RP Bio-Oil Shipment Tracker, batch Charm Contents, and applicable route Google Map? | PASS | Expanded the Certify Sources tab's "+5 more" listing on INJ-08-2026-W1 Ops Notes.xlsx and confirmed it is directly linked to the "QOWV Embodied Distance (CO to B6)" datapoint. CO to Basco Routing Map.png is also linked to the same datapoint. No standalone "Charm Contents" file exists -- the per-week workbook consolidates Ops Notes + Shipments/EE Allocation (which carries the per-PP mass breakdown) into one file, and that file is confirmed linked. Satisfies the Document Location Rule's intent. | Certify Sources tab; Document Location Rule
SECTION 7 — Certify Production Emissions (6 items, one aggregated component covering 4 PPs)
7.1 | Are there Production Emissions components for ALL Production Periods in the batch? | PASS | One aggregated component ("Pyrolysis - Charm QOWV PP Emissions") covers all 65 totes across all 4 Production Periods represented (November 2025, December 2025, January 2026, February 2026). Per FC-C2, aggregation into one mass-weighted component is acceptable -- no primary source requires per-PP component granularity. Mass (62,477 kg) reconciles exactly to the sum of Net Oil Produced across every PP-tagged row in the Ops Notes ledger. | FC-C2
7.2 | Does the CI match the correct CI basis for the removal's injection period? | FAIL | Certify "QOWV Pyrolysis Emissions - Carbon Intensity (Weighted)" = 0.1447 tCO2e/t. This is the Ops Notes' own weighted average of each tote's INDIVIDUAL MONTHLY Production-Period CI (Nov 2025 0.1392, Dec 2025 0.1631, Jan 2026 0.1568, Feb 2026 0.1330). Per the period VVB Guidance ("VVB Guidance July 1 - July 31", garrett.lutz@) and Max's confirmation (2026-08-25): beginning this Reporting Period, ALL Charm bio-oil removals injected through 12/31/2026 must use the blended H1 2026 mass-weighted CI, not each tote's individual monthly PP CI -- regardless of which historical month the oil was produced in. The correct blended QOWV CI (from V2_Charm_BioOil_Mass_Weighted_CI_Jan-Jun_2026.xlsx, Drive id 1J1_DxRBIbYTa3o65q_zEv_GSB6Ci6Pt8) is 0.120947 tCO2e/t. Recompute: 62.477 t x 0.120947 = 7,556.4 kg vs. the 9,040.55 kg currently reported -- production emissions are overstated by 1,484.1 kg (1.484 tCO2e), ~15.9% of net removal. | VVB Guidance July 1-31; project_charm_h1_2026_ci_policy
7.3 | Is the CI evidenced (period source for the applicable CI basis)? | PASS | Confirmed via the Certify Sources tab "+5 more" expansion that INJ-08-2026-W1 Ops Notes.xlsx is directly linked to the "QOWV Pyrolysis Emissions - Carbon Intensity (Weighted)" datapoint -- a source is linked for what Certify currently reports. The evidenced figure uses the wrong CI basis, but that is the substance of the 7.2 FAIL, not an evidence-linking gap; narrowly scoped here to "is a source linked" to avoid double-counting one root cause across two items. Once 7.2 is corrected, this citation will need to point to V2_Charm_BioOil_Mass_Weighted_CI_Jan-Jun_2026.xlsx instead. | Certify Sources tab
7.4 | Does the mass match the sum of Net Weight of Bio-Oil in Tote values for the PP(s) that apply to the component? | PASS | Certify "QOWV Pyrolysis Mass" = 62,477 kg. Ops Notes TOTAL Net Oil Produced (all 4 PPs, all 65 totes) = 62,477.00 kg. Exact match. | Certify component cmp_1M0FRSPSB1S0RPD5
7.5 | Does the uncertainty match the sum of uncertainties for the PP(s) that apply to the component? | PASS | Certify QOWV Pyrolysis Mass uncertainty = ±73.71 kg. Ops Notes TOTAL uncertainty (all 65 totes) = 73.7087 kg. Exact match. Uncertainty is present on this dominant emission input (9.04 t = ~97% of net removal), consistent with the requirement that a material input's uncertainty may not be omitted under the <1% carve-out. | Certify component cmp_1M0FRSPSB1S0RPD5
7.6 | Is the mass evidenced with a copy of the Charm Contents sheet for the batch? | PASS | Confirmed via the same Sources tab expansion that INJ-08-2026-W1 Ops Notes.xlsx is directly linked to the "QOWV Pyrolysis Mass" datapoint. Same resolution as 6.3 -- no standalone Charm Contents file exists, but the consolidated Ops Notes workbook (carrying the per-tote Production Period column) is confirmed linked. | Certify Sources tab; Document Location Rule
SECTION 8 — Other (1 item)
8.1 | Are all diesel transport-process emissions offset by BCUs, and does the BCU total >= the transport-process sum? | FAIL | Certify "BCU - Transport Process" is a hard-coded "Constant CO2 reduction" = 9,090 kgCO2e, evidenced by Charm-RetirementCertificate-RD-EACs-20251218.pdf. This was sized to exactly match the currently-reported (incorrect, tanker-EF) Transport Process emission of 9,090 kg. Once 5.1 is corrected to the Flatbed EF (11,006.6 kg), the existing 9,090 kg BCU would fall short of the corrected activity emission by 1,916.6 kg, violating the BCU >= transport-process-activity rule. The BCU needs to be resized (or a matching additional BCU retired) once 5.1 is corrected. | Certify component cmp_1M0FSKSV21S0Y8YT; KB §5 BCU QA Rule
SECTION 9 — Aqueous Buffering / LCS (1 item, Aqueous-only)
9.1 | If LCS use is reported in Ops Notes, does a matching Certify component exist? | N/A | No LCS / Liquid Calcium Sulfate column or reference found anywhere in the QOWV tab of INJ-08-2026-W1 Ops Notes. No LCS component present in Certify. Consistent -- N/A. | FC-C4
SIDEBAR OBSERVATIONS (no Pass/Fail status)
Net CDR impact of confirmed findings: Certify currently reports Net CO2e Removed = 9.321 tCO2e. Combined effect of 5.1 (Process EF, -1.917 t), 6.1 (Embodied EF, +0.091 t), and 7.2 (Production CI, +1.484 t) is a net UNDERSTATEMENT of total emissions by ~1.826 tCO2e -- meaning the currently reported 9.321 t net removal is likely OVERSTATED by a comparable margin once corrected (BCU resizing in 8.1 will also shift the result; exact corrected net CDR depends on how Garrett resizes the BCU and was not independently recomputed end-to-end).
This is the third consecutive QOWV batch (after INJ-07-2026-W1-QOWV and INJ-07-2026-W2-QOWV) to ship with Tanker Truck vehicle type selected instead of Flatbed/Non-Tanker for transport components. Worth raising with Garrett/ops as a template or removal-setup default that should be fixed at the source rather than caught and corrected batch by batch.
Uncertainty Discount on the Certify Calculation view = 81 kg (0.081 t) against a net removal of 9.321 t -- small relative to the magnitude of the EF/CI findings above.