## Operational Summary
Basco ToX — May 2026 Operational Summary — DRAFT FOR OPS TEAM REVIEW
Please review each row. Confirm status where marked 'Please confirm.' Provide answers where marked ⚠.
Active sparging | Ambiguous — review required | No sparging / maintenance
Period | Status (Tentative) | Basis (Data & Ops Notes) | Questions / Confirmation Needed | Ops Team Response
May 1 | No active sparging | Both trains below setpoint throughout. Train 2 blower offline for fan service. Operations focused on oil filtration and transfer of contaminated/thick AECN. | Please confirm: Was any sparging active on Train 1 during May 1?
May 2 (evening) – May 4 (afternoon) | Active sparging — Train 1 | Train 1 outlet at or above 600°F for ~30 operating hours across this window. Train 2 blower still offline throughout. | Please confirm.
May 4 (evening) – May 5 (evening) | Uncertain — Train 1 below setpoint; Train 2 blower restored | Train 1 outlet dropped below 600°F after the May 2–4 campaign. Train 2 blower returned from service ~May 5 evening. Neither train reached operating temperature. | ⚠ Were sparging blowers running during any part of this window? If yes — was the catalyst still above minimum inlet temperature even though the outlet reads below 600°F?
May 6 – May 8 | Uncertain — both trains below setpoint | Both trains below 600°F outlet throughout. Ops notes show oil transfers into sparging tanks and an injection event (May 7), but no sustained at-temperature ToX operation on either train. | ⚠ Were the sparging blowers running (i.e., active VOC stripping) during any part of this window? Temperature data cannot confirm this — please check shift logs or blower run records.
May 9 (3 AM) – May 11 (9:30 AM) | Planned maintenance shutdown | Both blowers offline for electrical wiring work. Both train sensors offline during this period. | Please confirm.
May 12 – May 23 | No active sparging | Both trains below setpoint for ~12 consecutive days. Ops reports confirm site was in thick oil remediation mode — shaking, filtering, moving oil. Thick oil challenge resolved ~May 22. | ⚠ Were there any sparging runs during this 12-day window? Temperature data shows no at-temperature operation on either train. Please confirm no sparging occurred, or flag any periods we may be missing.
May 23 (evening) – May 24 | Active sparging — both trains | Train 2 at temperature overnight May 23–24 (~24 operating hours). Train 1 at temperature afternoon May 24 (~12 operating hours). | Please confirm.
May 25 – May 31 | Intermittent sparging campaigns — both trains | Both trains show multiple at-temperature windows (see charts). Two events: system-wide pump shutdown May 30 (same-day restart); Train 1 SCFM flow probe fouled and cleaned May 31 (same-day). | ⚠ Can you identify which at-temperature windows in the chart represent active sparging campaigns vs. the oxidizer running with no active gas flow? The engineering brief explains this is difficult to determine from sensor data alone — shift logs or batch records would help.