This note sets out a working thesis for how Charm brings a bio-oil-derived Sustainable Aviation Fuel (SAF) pathway to market: certify eventually, but do not let full certification gate concept-proof or the first transactions. Start with a rigorous, transparent, non-certified “bolt-on” methodology that buyers and a registry will accept, and formalize the route to certification in parallel.

1. The end state is certification

To grow SAF from bio-oil into a mature, durable pathway, Charm will ultimately need formal certification. Certification is what unlocks the broadest market access and buyer confidence at scale.

2. The obstacle: cost, time, and a certified refinery partner

Full certification is demanding on time and internal effort, and — most challenging — it requires a certified refinery partner to co-process the bio-oil. That partner dependency is outside Charm’s direct control and cannot be manufactured on Charm’s timeline.

3. Principle: don’t gate the early work on full certification

Proving the concept, and even executing initial transactions, should not be saddled with the full weight and timeline of certification. The early phase needs a path that is credible and defensible without waiting on a certified refinery.

4. The interim approach: a non-certified “bolt-on” methodology

Charm starts by transacting on the non-certified bolt-on methodology — Charm’s validated CDR “root” (biomass qualification through pyrolysis co-product CI) with a reputable, published downstream methodology bolted on for co-processing — provided two conditions are met:

Buyer acceptance. Amazon (et al.) is comfortable with the non-certified method, provided Charm shows its work in full.

Registry acceptance. Either Isometric or 123Carbon is willing to host the SAF environmental attributes.

4a. Scenario A — Isometric hosts the SAF attributes

If Isometric stands up a SAF pathway, it develops the SAF methodology itself. That fits the bolt-on cleanly, because Isometric also owns the “root” — the validated CDR methodology Charm already runs. The registry that owns the root authors the branch, so there is no separate need to formalize the bolt-on through a third-party developer, that workstream shifts to Isometric.

4b. Scenario B — 123Carbon hosts the SAF attributes

The claim runs on 123Carbon’s SFC MBM framework. Because 123Carbon does not own the root, Charm builds the bolt-on itself: it engages a third-party methodology developer to formalize the bolt-on into a verifiable methodology document.

“Show our work” has a concrete bar: a transparent, documented methodology, independent third-party verification, and full disclosure to the buyer/registry. Non-certified does not mean unverified.

Double-counting between the CDR and SAF claims is handled by a physical inventory split: bio-oil is allocated by physical tonnage to each stream. For example, of 10 tonnes of bio-oil, 6 tonnes sent to SAF leaves 4 tonnes for CDR — the two claims never rest on the same physical material.

5. Eventual certification target: ISCC PLUS

The certification we build toward is ISCC PLUS. The deciding factor is refinery availability in the United States: there are currently no RSB-certified refineries doing co-processing in the U.S., versus roughly five or six ISCC-certified ones. Because the certified-refinery partner is the hardest dependency, the scheme with an existing U.S. certified-refinery base is the pragmatic target.

6. Next steps

Charm issues an RFP for a qualified third-party methodology developer to deliver two things:

Confirm conditions for bolt-on are met

123 Carbon will register non-certified credits given buyer is comfortable

Amazon will buy non-certified credits given a registry to manage them

Engage Isometric with a near-term goal of pressure-testing alignment on carbon accounting must-haves (e.g. flexible allocation/mass balance)