## Tracker
ID | Section | Ask / Topic | Module / Surface | Status | Latest | Pointer
A1 | A. Bio-oil alt-use | Bio-oil → SAF via FCC coprocessing — attributional vs consequential carbon accounting; EAC / molecular-attribution ('free allocation') framework. C14 attribution is the technical blocker. | New module surface; touches GHG Accounting and ICAO/CORSIA crosswalk | ACTIVE | Isometric returned written questions on attributional vs consequential; Peter has commented on the doc. | #oil-materials; doc 1-42aKEo0...
A2 | A. Bio-oil alt-use | Bio-oil → marine fuel via hydrotreating (VTT / Honeywell-UOP path). | Same accounting surface as A1 — drop-in fuel rather than geological storage | EXPLORATORY | VTT proposal received covering FCC coprocessing, marine fuel hydrotreating, lab-scale SAF. | #oil-materials
A3 | A. Bio-oil alt-use | Bio-oil → asphalt binder / bio-pitch. Tim 'stoked about asphalt binder' (can be paired with biochar in same product); Global Emissionairy requested bio-oil emulsion samples for asphalt blending; Hull's railcar-oil-as-binder precedent. | Substitution method (Procedure 3) candidate; needs binder-specific reference product + EF | EXPLORATORY | Sample requests live; no Charm position yet. | #oil-materials; #char-industry
A4 | A. Bio-oil alt-use | Bio-oil → ironmaking DRI (distinct from biochar EAF/BF — gas-phase reductant). | New module surface; pairs with iron-and-steel book-and-claim (D2) | EXPLORATORY | GTI engaged for R-GAS + Aspen flowsheet modeling at ~$200k. | #ironmaking-dri; #steel
B1 | B. Biochar alt-use | Biochar-as-coal in cement kiln — predict-and-adjust framework for substitution method, 0% uncertainty discount, evidence package. | GHG Accounting Module §6.1 (Procedure 3 vs 4 interaction) | SETTLED | Alignment closed 2026-03-31. Operating under exemption note until §6.1 module text update is published. | biochar-cement-substitution/Implementation_Brief.docx; #isometric-charm
B2 | B. Biochar alt-use | Substitution method residual items — three marginal pushbacks: (a) pilot-PP edge case, (b) per-PP biochar characterization burden, (c) upstream coal emissions in counterfactual (combustion-only is not enough; Brian's pushback). | GHG Accounting §6.1 follow-on | QUEUED | Flagged in #char-industry as 'marginal items still to push back on in the next round.' Brian's upstream-coal point not yet escalated. | #char-industry; #isometric-charm
B3 | B. Biochar alt-use | Biochar physically embedded in concrete (ZeroTwelve, AlterBiota, Solid Carbon/NLR, Mike Griffin). Different from B1 — char becomes part of the product, not combusted. | New methodology surface — likely not B1 substitution method. May not run through Isometric if EAC ambiguity (E1) holds; Harris asked Brian to scope Carbon Direct / EcoEngineers / WSP for proto-verification as fallback | EXPLORATORY | D-Series 28-day concrete strength data pending. AlterBiota ASTM C494 admixture qualified. | #char-industry; #sales_amazon
B4 | B. Biochar alt-use | Biochar in iron & steel — EAF coal injection, BF-BOF PCI substitution, DRI biochar. Brian offered Isometric a co-study on a 'char for coal substitution proto-protocol (cement, BF, EAF).' | Substitution method extension + iron-and-steel book-and-claim layer | ACTIVE | RMI Steel Book and Claim consultation response submitted 2026-04-30 (Brian-led, Max review). ArcelorMittal Dofasco pilot in flight. EPD generation flagged as a prerequisite. | #ironmaking-dri; #char-industry; #steel
B5 | B. Biochar alt-use | Biochar in anaerobic digesters — CDR retention via digestate end-fate (AZ / Vanguard play). | BSSE v1.2 carve-outs for digester partition, post-AD permanence, digestate land-app safety | PARKED | Internal MRV memo 2026-05-04 recommends commercial-only; (b) parked as multi-quarter R&D. AZ deal pressure could force re-activation. | Biochar_in_Anaerobic_Digesters_MRV_Position_2026-05-04.docx
B6 | B. Biochar alt-use | Avoided-methane / super-pollutant credit stacked on biochar CDR (Plasek pitch). | New super-pollutant module that biochar can plug into | PARKED | Multi-year work; double-counting against Vanguard's RIN/LCFS. Track, do not invest. | #mrv-protocol
C1 | C. BSSE v1.2 | Storage in absence of wetting — Fauske isothermal basket negative result; supersacks under weatherproof cover; per-product self-heating evaluation gate. | BSSE v1.2 §7.3 / G-TGR7-0 exemption | SETTLED | Closeout 2026-04-27; exemption note to be issued at next verification. | Charm_Response_to_Isometric_Biochar_v1.2_Closeout.docx
C2 | C. BSSE v1.2 | End-use evidence pathway — §8.5.2 Project Boundary Mapping with Application Records, not §8.5.1 geotagged photo essay. | BSSE v1.2 §8.5 | SETTLED | Same closeout. Brenner back-fill via written attestation. | Charm_Response_to_Isometric_Biochar_v1.2_Closeout.docx
C3 | C. BSSE v1.2 | 24-month stockpiling window (vs 12-month default). | BSSE v1.2 §7.3 duration | SETTLED | Same closeout. Verbal reservation kept on per-verification carve-out for legacy inventory. | Charm_Response_to_Isometric_Biochar_v1.2_Closeout.docx
C4 | C. BSSE v1.2 | PAH testing carve-out via §3.3 mitigation pathway — initial validation + prior-process evidence (BSK Associates 15/16 priority PAHs <200 µg/kg) instead of per-batch testing. | BSSE v1.2 §3.3 Table 2 footnote | QUEUED | Bundled in pre-confirm note to Tom; ready to send. | Charm_Isometric_BSSE_v1.2_Implementation_PreConfirm.docx
C5 | C. BSSE v1.2 | Soil temperature methodology — Lembrechts et al. 2022 / SoilTemp dataset rather than per-site monthly campaigns. 7°C floor, 1°C boundary subdivision rule applied as written. | BSSE v1.2 §5.1.2.2.1 (Option 1, 200-yr durability) | QUEUED | Same pre-confirm bundle. | Charm_Isometric_BSSE_v1.2_Implementation_PreConfirm.docx
C6 | C. BSSE v1.2 | Lab accreditation regime — periodic external validation if Soil Control Labs not fully ISO 17025 covered for Charm's methods (proposed: one validation set per crediting cycle). | BSSE v1.2 §3.1, §4.1.2 | QUEUED | Same pre-confirm bundle. SCL accreditation status check is the gating dependency. | Charm_Isometric_BSSE_v1.2_Implementation_PreConfirm.docx
C7 | C. BSSE v1.2 | Third-party composter sales precedent — verified composter deliveries under v1.1 should not require v1.2 §8.7 affidavit/business-history layer. | BSSE v1.2 §8.7 / Standard v2.0 §2.4.2 | QUEUED | Argued in Apr 1 Response; status of Isometric's acceptance unclear in closeout doc. Worth confirming explicitly. | Charm_Response_to_Isometric_Biochar_v1.2_Review.docx
D1 | D. Bio-oil ops | Decoupling durability monitoring from verification — 60-day filing window (vs 30); non-rhythmic test scheduling; reversal investigation workflow; Monitoring Statement deliverable; single VVB engagement. | Bio-oil Geological Storage protocol — operational agreement (not module bump) | ACTIVE | Charm response sent 2026-05-01. Awaiting Isometric draft of operational agreement. | Charm_Response_to_Isometric_Decoupling_Monitoring_from_Verification.docx
D2 | D. Bio-oil ops | Charm-side CI tenure → 6 months for WODO / Aqueous / biochar (mirrors AECN's half-yearly cadence). | Same instrument as D1 | ACTIVE | Embedded in D1 response §3. Aligns three currently-misaligned cadences (AECN CIs, Charm CIs, monitoring submissions). | Charm_Response_to_Isometric_Decoupling_Monitoring_from_Verification.docx
D3 | D. Bio-oil ops | BOL as sole authoritative mass for direct-trucked AECN — retire receiving-side empty/full scale weighing. | Bio-oil Mass Quantification Program | QUEUED | Position paper drafted Apr 2026. Materiality cleared under GHG Accounting v1.0 §5.0 (+0.133% aggregate). Rail carve-out preserved. | Charm_Position_BOL_Authoritative_Mass.docx
D4 | D. Bio-oil ops | Rail-offloaded BOL-only treatment — parallel to D3, pending more rail-leg data. | Bio-oil Mass Quantification Program | QUEUED | Garrett drafted rail mass-accounting memo following same MIN(BOL, scale) logic. Position paper on full BOL-only treatment is a follow-up to D3. | #mrv-ops-la
D5 | D. Bio-oil ops | Time-block batching — administrative reorganization of injection data batching (one week vs per-injection). | Operational change to current batching convention | ACTIVE | First submitted 2026-03-16. As of QBR draft (4/13), still unresolved past 2x SLA. As of 2026-05-08, still chasing in #isometric-charm. | #isometric-charm; QBR brief
E1 | E. EAC posture | Reconcile mixed signals on Isometric's EAC posture — Harris's note (2026-04-27) says Isometric 'dropping out of the EAC registry game'; Peter's meeting with Eamon CEO + Chris Podgorney says Isometric is 'exploring EACs broadly including cement, steel, SAF.' Brian's reaction: '100% not where I thought we landed.' This is gating for every drop-in / substitution / book-and-claim pathway above. | Cross-cutting on A1, A4, B3, B4 | ACTIVE | Needs direct re-engagement. Until clarified, alt-use pathways above sit on uncertain ground. | DM with Brian; #char-industry
F1 | F. Biomass feedstocks | Sugarcane bagasse (Cajun) | BFA v1.3 + One Affidavit to Rule Them All | SETTLED | Cleared Isometric pre-validation; shipped to legal. | #biomass-working-group
F2 | F. Biomass feedstocks | Corn stover / wheat straw (Hickory) | BFA v1.3 — SUR safeguard against market leakage | ACTIVE | MRV 'a good deal more complicated'; affidavit drafted. | #biomass-working-group
F3 | F. Biomass feedstocks | Sawmill residuals (Cajun) | BFA v1.3 | QUEUED | Cleared 10% milestone; pre-validation memo + uPyro testing in queue. | #biomass-working-group
F4 | F. Biomass feedstocks | Forest biomass — CO wildfire / private-land fuels reduction | BFA v1.3 §SC1.2, SC1.3, CC2 (gov't-managed wildfire mitigation exemption) | QUEUED | Interpretive guidance request drafted Apr 2026. Includes proposed evidence guardrails (CWPP alignment, forester prescription, etc.). | Charm_Forest_Biomass_Evidence_Guidance_Request.docx
F5 | F. Biomass feedstocks | Biomass pre-validation process itself (standing Charm-Isometric interface for new feedstock onboarding) | Process, not module text | SETTLED | Established with Isometric; running through Tom Sellers / biomass-working-group. | #biomass-working-group
G1 | G. QBR process | SLA adherence on project change proposals — proposed: Registry Ops briefs science team before cold handoffs, or pulls them into scoping calls. | Partnership process | ACTIVE | Raised in Q2 2026 QBR brief. | Charm_Isometric_QBR_Brief_Q2_2026.docx
G2 | G. QBR process | CCP labeling timeline gaps — proposed: don't certify a module update until the new version also carries CCP labeling; registry coordinates with ICVCM, not developer. | Partnership process | ACTIVE | Raised in Q2 2026 QBR brief. | Charm_Isometric_QBR_Brief_Q2_2026.docx
G3 | G. QBR process | Module versioning & change management — proposed: structured developer consultation period before public consultation/certification; minimize update frequency. | Partnership process | ACTIVE | Raised in Q2 2026 QBR brief. | Charm_Isometric_QBR_Brief_Q2_2026.docx
H1 | H. Adjacent (not Isometric) | Biochar N₂O suppression revenue path — internal memo concludes Scope 3 / insetting via row-crop offtakers (Indigo, Truterra, Bayer, Cargill RegenConnect, ADM, Land O'Lakes), not a new Isometric module. | Scope 3 / SBTi FLAG / GHG Protocol Land Sector | PARKED | Internal memo dated 2026-05-06. | Biochar_N2O_Scope3_Revenue_Path_2026-05-06.docx
H2 | H. Adjacent (not Isometric) | Biochar N₂O via Verra VM0042 v2.2 — Harris flagged Verra ALM module (CCP-Approved Nov 2025) may credit biochar N₂O on agricultural land; not Isometric. | Verra VM0042 v2.2 (ALM) | EXPLORATORY | Harris raised in #char-agriculture. | #char-agriculture
H3 | H. Adjacent (not Isometric) | Carbon Direct / EcoEngineers / WSP proto-verification for biochar-in-cement (B3) — fallback if Isometric EAC posture (E1) doesn't land. | Proto-verification (non-Isometric) | EXPLORATORY | Harris asked Brian to scope. | #char-industry

## Legend
Status | Meaning
ACTIVE | Submitted to Isometric, awaiting their response, or in active back-and-forth.
SETTLED | Alignment reached with Isometric; awaiting module text update or exemption note at next verification.
QUEUED | Drafted internally, not yet sent to Isometric.
EXPLORATORY | Early conversations, no formal Charm position yet.
PARKED | Out of immediate scope; track for re-activation.

## Maintenance
How to maintain this tracker
1. Update the 'Latest' column when a status changes — date + one sentence.
2. New row whenever a new ask surfaces in Slack, Drive, or correspondence. Do not wait for a formal deliverable; exploratory threads count.
3. When an item moves to SETTLED with module text published, leave the row in place but add the published-text reference. Do not delete — provenance matters when verifiers ask 'since when?'
4. Cross-links: many rows depend on E1 (EAC posture) and on the §6.1 substitution-method machinery from B1. When you update one, sweep dependents.
Companion markdown file: outputs/mrv-operational-documents/Isometric_Module_Push_Tracker.md