## Commissioning Checklist
New-Generation Pyrolyzer — MRV Commissioning Checklist (INTERNAL)
Charm-produced streams (bio-oil WODO/Aqueous + biochar). Complete before reporting any removals from the new units. Owners/targets to be assigned. Protocol refs: BioOil = Bio-oil Geological Storage v1.2; BioP&S = Biochar Production & Storage v1.2; SoilEnv = Biochar Storage in Soil Environments v1.2; EUA = Energy Use Accounting v1.3.
# | Task | Detail / acceptance criteria | Protocol reference | Owner | Target | Status | Notes
1. Updated reactor details (→ PDD & re-validation)
1a | Design diagrams | Dimensions, material in/outflows, temperature & pressure sensor positions, internal & external equipment. Replaces PDD Figures 1a/1b. | BioP&S §9.2.1 |  |  | Not started
1b | Materials + resilience justification | Per reactor component; thermal & mechanical. | BioP&S §9.2.2 |  |  | Not started
1c | Confirm operating pressure regime | Sub-atmospheric? If NOT → add continuous gas-loss/leakage monitoring. If >~0.5 Bar over ambient → pressure range/limits, vessel shape/size, inlet/outlet positioning, pressure-vessel standard compliance. | BioP&S §9.2.2 (pressure vessel); §10.1.3 (gas-loss monitoring) |  |  | Not started
1d | Reactor maintenance plan |  | BioP&S §9.2.3 |  |  | Not started
2. PDD updates (specific v1.12 locations)
2a | Appendix 11 — reactor spec + Figures 1a/1b | Replace updraft-gasifier / 83 kg-hr / A36+ceramic / 800°C / sub-atmospheric spec for the new generation. | BioP&S §9.2.1 (updated diagram required); PDD App 11 |  |  | Not started
2b | Section A — facility & scale description | Pyrolysis-locations list, throughput narrative. | BioP&S §9.1 (reactor type/scale in PDD); PDD Sec A |  |  | Not started
2c | Section B — pyrolysis emission rows | Fuel use, electricity use, stack/tail-gas, embodied equipment (all 'Charm' rows). | BioP&S §8.6.5.5 (energy), §10 (tail-gas), §8.6.5.7 (embodied); BioOil §8.5.6 |  |  | Not started
2d | Appendix 11 — Production Period definition | New generation = new Production Period ('consistent pyrolyzer setpoints'). | BioOil §8.3.1.1 (new Production Process on significant change); PDD App 11 |  |  | Not started
2e | Appendix 11 — durability method | Update reported molar H:Corg that feeds Fdurable. | SoilEnv §5.1.2.2.1 (Option 1); §3.3 Table 2 |  |  | Not started
2f | Cross-references to superseded design docs | Point reactor/stack-emissions references off v1.7/v1.8 of the older Kansas design document. | BioP&S §9.2.1 (config must reflect validated reactor) |  |  | Not started
3. Biochar characterization (new-gen char)
3a | Permanence characterization | GO / NO-GO: molar H/C_org < 0.5 AND O/C_org < 0.2. If either fails, the char is not creditable under the storage module — characterize before committing production. | SoilEnv §3.3 Table 2 (thresholds); §5.1 (durability) |  |  | Not started
3b | Contaminants screening | Heavy metals (Pb 300 / Cd 5 / Cu 200 / Ni 100 / Hg 2 / Zn 1,000 / Cr 200 / As 20 g/t DM); PAH (EPA-16 declaration, EFSA-8 ≤1 g/t DM); PCDD/F ≤20 ng/kg DM; PCB ≤0.2 mg/kg DM. | SoilEnv §3.3 Table 2 |  |  | Not started
4. Emissions testing
4a | Accredited tail-gas / stack test on new machine | Per feedstock; scale by biomass throughput. ONE test on the shared machine; result allocated across bio-oil and biochar. | BioP&S §10.1 / §10.1.1.2 (±10% representativeness); BioOil §8.5.6 |  |  | Not started
4b | Confirm gas end-use route | Current: non-condensable gas co-fired with propane for biomass drying — reconfirm for new units. | BioP&S §10.1.2 (four permissible routes) |  |  | Not started
5. Biochar wet storage (self-heating change)
5a | Confirm storage basis change | New char fails the self-heating (Fauske) screening underlying current dry-storage handling. | SoilEnv §7.3 (stockpiling safety) |  |  | Not started
5b | Wetting SOP + PDD stockpiling section | Wet or moist-compost; covered/weatherproof; sited away from waterways; ≤12-month stockpile. Detail location + mitigations in PDD. | SoilEnv §7.3 (wet storage; PDD documentation; 12-mo) |  |  | Not started
5c | Transport reclassification | With EHS — UN self-heating class + handling controls. | SoilEnv §7.3 (driver); transport class is external (UN/DOT), not an Isometric section |  |  | Not started
6. Accounting & embodied emissions
6a | Re-baseline energy use → new process emission factor | Electricity + fuel for the new units (reactor heating, start-up, drives, handling). | BioP&S §8.6.5.5; EUA v1.3 |  |  | Not started
6b | Re-run co-product allocation (energy content) | New yield split changes the bio-oil / biochar / gas fractions. | BioP&S §8.6.5.4.1; BioOil §8.5.5.1.1 |  |  | Not started
6c | Embodied-emissions inventory | Add new equipment as commissioned; existing units amortize out until fully depreciated. | BioP&S §8.6.5.7; BioOil §8.5.5 (embodied) |  |  | Not started
6d | Certify build | New-generation components incl. tail-gas; re-derive per-datapoint uncertainty inputs. | BioOil §6.5 / BioP&S §6.5 (Uncertainty); Certify entry is platform, not a protocol section |  |  | Not started
7. Isometric / VVB
7a | Send the MRV note; align scope & sequence | Charm_New_Pyrolyzer_Generation_MRV_Note.docx. | BioP&S §6.1 (PDD) / §6.2 (Validation & Verification) |  |  | Not started
7b | Confirm validation path | PDD amendment (retains validation) vs. broader re-validation. | BioP&S §6.2 (Validation & Verification); §9.2.1 |  |  | Not started