Biweekly Check In Agenda

Great Turnarounds

–  BOL-only mass for direct AECN trucks

–  Initial forestry ask

Verification Post-Mortem

Underlying concern: trend reversal in verification turnaround time

| Jan | Feb | Mar | Apr |
| --- | --- | --- | --- |
| 16 days | 8 days | 5 days | 14 days |

Root Cause Analysis

350 Scheduling / Availability  →  Dead Time

Submission:  May 13

Initial findings:  May 17  (3 days lost)

Dead air:  May 17 – May 22  (5 days lost)

"Piecemealing" of Findings

–  Closed out initial batch of 7 findings within 2 days of receipt

–  Additional FAR note did not arrive until May 22 — 9 days after submission, 5 days after initial findings

Separation of Removal Verification and Accounting Policy Questions

–  Embodied emissions amortization

·  Impacts Net CDR calculations marginally

·  If Charm's broader system-optimization plans had been known, would not have been raised as a finding

–  Feedstock re-validation policy

·  Time-zone differences added a full day to resolution

Missed TOx FAR

–  Project management miss on Charm's end

–  Resolved in ~2 hours once identified

Requests

–  350 is scheduled to be available for end-to-end verification within 48 hours of submission

–  Verification is not paused due to other 350 engagements

–  Findings are returned in one consolidated batch — not piecemealed

–  Separate pathway for accounting policy questions vs. removal verification findings

·  This would dovetail with the 6-month cadence shift

·  An interim solution would be valuable ahead of that transition

Questions for Isometric

–  What is Isometric's approach to scheduling and managing 350 engagements?

–  Does Isometric have an SLA or similar requirement covering 350 engagements? If so, what does it entail?

–  Have other projects experienced similar delays? What improvement or resolution practices have been effective?

6-Month Transition — Status

Opened:  May 5

Initial response:  May 12

Remaining Open Items

–  Align §2.3 with 350

–  Align Section 3 (6-month Charm CI)

Upcoming

–  New evidence format for time-block batching

–  Forestry dummy evidence

–  EE reconciliation in progress — update planned mid-June

–  Targeting June 10 submission for May removals

–  Char substitution pre-agreement plan