## README
Charm Industrial — BSSE v1.2 Compliance Project Plan
Owner: Max Lavine ¦ Drafted: May 2026
Background
March–May 2026 Isometric review of Biochar Storage in Soil Environments v1.2 closed on May 5, 2026. Three resolutions: (1) Isometric will issue an exemption note from the wetting requirement at next verification, conditioned on Charm's storage-in-absence-of-wetting proposal; (2) end-use evidence follows the §8.5.2 Project Boundary Mapping with Application Records pathway, not the geotagged-photo §8.5.1 pathway; (3) stockpiling duration window is 24 months (vs. 12-month default).
Adoption of BSSE v1.2 also forces companion adoption of Biochar Production and Storage v1.2, Standard v2.0, Biomass Feedstock Accounting v1.3, Energy Use v1.2, Transportation v1.1, and Embodied v1.0.
Next biochar reporting period expected Q2/Q3 2026 after the next two truckloads ship. BSSE v1.2 protocol-level adoption deadline is November 14, 2026 — outside guardrail. VVB is Kelly @ 350 Solutions.
Compliance discipline
Per BSSE v1.2 §1.3, the protocol distinguishes 'must' / 'required' (mandatory) from 'recommended' / 'may' / 'should' (best practice). Sheet 1 of this plan contains only items the protocol marks as mandatory, plus operational items required to deliver on the exemption Charm has agreed to with Isometric (e.g., the storage-in-absence-of-wetting SOP that the wetting exemption is conditioned on). Sheet 2 captures items the protocol marks should/may/recommended — explicitly EXCLUDED with reason and revisit conditions. Volunteering should/may items expands the verifier audit surface without compliance return; we don't volunteer.
Sheet structure
• Sheet 1 'Required (Must)' — the actual project plan; only must-do items
• Sheet 2 'Excluded (Should-May)' — items deliberately not pursued, with citation, mandate, and revisit conditions
• Sheet 3 'Open Dependencies' — blockers gating sheet 1 items
Workstreams (color-coded in Sheet 1)
• Ops (yellow) — operational compliance, must land before next RP
• PDD (green) — Appendix 11 rewrite (Charm Industrial Bio-Oil Geologic Storage + Range & Plains Biochar PDD, Appendix 11)
• External (orange) — engagement with Isometric and VVB
Companion deliverables produced alongside this plan
• Charm_Biochar_Supply_Agreement_Template_v1.2.docx (outputs/mrv-operational-documents/biochar-offtaker-agreement-clauses/)
• Charm_Isometric_BSSE_v1.2_Implementation_PreConfirm.docx (outputs/deliverables/isometric/)

## Required (Must)
ID | Workstream | Task | BSSE v1.2 Citation | Owner | Target Date | Status | Notes
A1 | Ops | Storage SOP for biochar held in absence of wetting: supersack + cover + waterway-proximity avoidance; Fauske isothermal-basket negative-result basis; per-new-product self-heating evaluation gate (every new feedstock x pyrolyzer combo, EHS sign-off before stockpile use) | §7.3 | Brian + Rachel |  | Not started | Substantive content of the Isometric exemption note. Without this SOP the wetting exemption has no basis to issue against.
A2 | Ops | Revised Charm Biochar Supply Agreement template — single document covers §8.5.2 (direct-to-soil application records) and §8.7 (third-party sales / affidavit content) | §9.5.2, §9.7.1, §9.7.2, §9.2.2 | Katie + MRV |  | Drafted | Drop-in for Katie's redlines is at outputs/mrv-operational-documents/biochar-offtaker-agreement-clauses/. Brenner needs separate written attestation for back-fill (existing executed agreement).
A3 | Ops | Application records database (system of record): per-event logbook with Application Location (street address or GPS), application date or date range, dry mass applied, estimated acreage, computed application rate, link to Charm storage-batch ID. No GIS layer required — location is just a field. | §9.5.2 | MRV (spec) → Ops (operate) |  | Not started | MRV designs the data model to §9.5.2 evidence requirements; Ops takes operational ownership for population and maintenance. Owner handoff is an open dependency.
A4 | Ops | Chain-of-custody system: unique sequential storage-batch IDs from production through delivery; dispatch / receiving / BOL / delivery-receipt records all linked to batch ID; COC diagram for the PDD | §9.9 | Ops + Jackson |  | Not started | Manufacturo integration. Output for the PDD: COC diagram + 5-yr record retention policy.
A5 | Ops | Inventory aging tracker: production date tagged on every supersack; reporting view that surfaces inventory approaching the 24-month exemption window | §7.3 | Ops + Jackson |  | Not started | Manufacturo-based. Loss accounting per parent §8.4.1.2 — biochar reversed during stockpiling stays within project boundary.
A6 | Ops | Characterization gap-close: confirm next-batch lab panels run the v1.2 required parameter set — N, S, salt content, bulk density (<3 mm fraction), nutrient declaration (P, K, Mg, Ca, Fe), pH | §3.3, App I Table 2 | Steven + Brian |  | Not started | Already covered: Total C, Inorganic C, H, O, ash, moisture, H/Corg, O/Corg, heavy metals, PAHs, PCBs, PCDD/F. WHC is recommended only — excluded.
A7 | Ops | Lab accreditation confirmation: confirm Soil Control Labs holds ISO 17025 (or equivalent) for our analytes. If not, propose periodic external-validation regime to Isometric (one split-sample set per crediting cycle at an accredited reference lab) | §3.1, §4.1.2 | Steven + Brian |  | Not started | Eurofins (PCB/PCDD/F) and BSK (PAH via NELAP) are accredited — no action. Issue is bundled into pre-confirmation note to Tom (C2).
A8 | Ops | Offtaker handling and application best-practice guide: short PDF given to every direct-to-soil customer covering handling, application, dust, moisture, fire/safety | §6 (must for direct-to-soil) | Rachel + Brian + Katie |  | Not started | Required for direct-to-soil offtakers. Industrial and ag use cases both covered.
P1 | PDD | Update version refs throughout: BSSiAS v1.1 → BSSE v1.2; Standard v1.7 → v2.0; Biomass Feedstock Accounting → v1.3; Energy Use → v1.2; Transportation → v1.1; add Embodied v1.0 | Throughout | Max |  | Not started
P2 | PDD | §1.3 acknowledgement statement — proponent acknowledges must/required vs recommended/may/should distinction and confirms ability to meet mandatory requirements | §1.3 | Max |  | Not started | One-paragraph stub.
P3 | PDD | §1.1 / §2.1 site eligibility declaration: no land-management practice would pose risk greater than ag soils; pre-existing heavy metals screening (only required if encountered) | §1.1, §2.1 | Max |  | Not started
P4 | PDD | Lab accreditation: explicit ISO 17025 (or equivalent) status documented per lab and analyte | §3.1, §4.1.2 | Max |  | Not started | Gated on A7.
P5 | PDD | Required characterization parameters table — full v1.2 required set with method refs (ISO/ASTM/DIN), n=3 frequency, thresholds where applicable | §3.3, App I Table 2 | Max |  | Not started
P6 | PDD | PAH testing carve-out invocation per §3.3 footnote — document the technical basis (high-temp pyrolysis with continuous tailgas evacuation, controlled feedstock, prior NELAP-accredited testing evidence) | §3.3 footnote | Max |  | Not started | Invoking saves recurring per-batch PAH lab cost. Gated on Tom confirm (C2).
P7 | PDD | Sampling plan: Method A, n=3 replicates per batch, documented horizontal/vertical heterogeneity sampling per §4.1.1 | §4.1, §4.1.1 | Max |  | Not started
P8 | PDD | Data reporting and retention: 5-year records retention; sampling regime summary in PDD; data report includes analytical uncertainty, sample/standard counts, std deviation, percentage error | §4.3 | Max |  | Not started
P9 | PDD | Tsoil methodology: pin to Lembrechts et al. (2022) or the equivalent agreed with Isometric; document 7°C conservative floor; document 1°C boundary-subdivision rule; document why air temperature is not used as proxy | §5.1.2.2.1 | Max |  | Not started | Gated on Tom confirm (C2). Project-specific monthly soil-temp campaigns are operationally unworkable across our offtaker network.
P10 | PDD | Site selection — must-gates only: no spreading on land frozen >12 hr in prior 24 hr; no spreading where >50% snow cover; no spreading on waterlogged soil; no spreading on steep slopes without erosion preventative-measures evidence | §5.2.2.1 | Max |  | Not started | Application-side 10 m / 50 m setbacks are 'should' — excluded. Stockpile-side waterway proximity avoidance lives in A1.
P11 | PDD | §7.3 stockpiling narrative: stockpiling location, supersack/cover, 24-month duration window with explicit reference to Isometric exemption note; Fauske-negative basis; per-new-product self-heating evaluation policy; loss accounting per parent §8.4.1.2 | §7.3 | Max |  | Not started | Mirrors A1 SOP content in PDD form.
P12 | PDD | §7.2 post-deployment fuel-use risk: short justification — Charm offtaker base and product form factor present no material picking-for-fuel risk; declared zero | §7.2 | Max |  | Not started
P13 | PDD | Evidence pathway declarations per §9.1: explicitly name §8.5.2 (direct-to-soil — application records DB) and §8.7 (third-party sales — affidavit clauses in supply agreement, sales documentation, proof of delivery). List specific evidence package per pathway. | §9.1 | Max |  | Not started
P14 | PDD | Chain of custody: diagram, unique batch ID system, handoff documentation, 5-yr retention | §9.9 | Max |  | Not started
P15 | PDD | Document History: add v2.0 row (date + 'BSSE v1.2 + Standard v2.0 alignment') | n/a | Max |  | Not started
C1 | External | Confirm exemption-note wording with Tom Sellers: (a) wetting absence + Charm storage proposal, (b) 24-month stockpiling window. Get both into Isometric items log so VVB sees them at next verification | §7.3 (mandate basis) | Max |  | Not started
C2 | External | Combined pre-confirmation note to Tom covering: (i) PAH testing carve-out invocation, (ii) Tsoil methodology (Lembrechts 2022 or equiv), (iii) lab accreditation regime if SCL not fully ISO 17025 | §3.1, §3.3, §5.1.2.2.1 | Max |  | Drafted | Drafted at outputs/deliverables/isometric/Charm_Isometric_BSSE_v1.2_Implementation_PreConfirm.docx — ready for Max review and send. Gates P6, P9, A7.
C3 | External | Brief Kelly @ 350 Solutions on v1.2 deltas, exemption notes, new evidence pathways, new characterization panel | n/a | Max |  | Not started | Target: 30 days before next RP.
C4 | External | Lock next biochar reporting period dates (start, cutoff, verification window) | n/a | Max + Ops |  | Not started | Once next two truckloads scheduled.

## Excluded (Should-May)
ID | Item | BSSE v1.2 Citation | Mandate | Reason for exclusion | Revisit if?
X1 | Sample archiving — retain 100 g representative dried subsample per production batch for ≥5 yr | §4.3 | Recommended | Not protocol-required. Adds ongoing storage and tracking work that doesn't gate any audit outcome we currently face. | Verifier audit asks for re-analysis of a prior batch.
X2 | Site management parameter reporting in GHG statement — irrigation schedule, irrigation source, tillage practice, fertilizer/amendment usage and composition, vegetation, pre/deployment/post monitoring | §5.2.1 | Should | Volunteering this expands the verifier audit surface for content the protocol does not require. Each field volunteered is one more thing the VVB can hold against us. | Isometric or VVB explicitly requests it.
X3 | Soil baseline establishment at offtaker sites — pH, soil moisture, bulk density, soil type/texture, nutrient availability, SOC, 3-yr crop yield | §5.2.2 | Should | Constrained by offtaker willingness to share. Not required for crediting under Option 1 200-yr durability. Would add an offtaker-engagement burden with no compliance return. | Sustained crop-yield decrease (>3 yr) trigger fires under §2.1, or strategic decision to pursue a tighter durability claim.
X4 | Co-benefits voluntary reporting in PDD — crop rotation, yields, soil quality, fertilizer use | §2.2 | May | Not required. Volunteering expands narrative scope and verifier audit surface without strengthening the durability or evidence claim. | Buyer-side or marketing ask justifies it.
X5 | Production Period / Production Batch terminology mapping in PDD | n/a | Internal clarity — not protocol-required | Charm's Production Period / Production Batch convention is operationally correct; if the VVB raises confusion it can be addressed via cover note rather than PDD edit. | VVB raises terminology question at validation.
X6 | Pre-validation walkthrough of Appendix 11 with Isometric before VVB sees it | n/a | Risk reduction — not required | C2 pre-confirmation note covers the items most likely to cause issues. A second walkthrough is duplicative unless C2 surfaces unexpected concerns. | C2 response from Tom raises material concerns that warrant a deeper review.
X7 | Data reporting in 4-dataframe format (summary metadata / reduced data / processing / raw) | §4.3 | Example pattern — not mandate | §4.3 says 'For example, this may take the form of...' — illustrative, not required. Submit data in whatever clean format we already use. | VVB rejects current format.
X8 | Application-side setbacks: 10 m from any watercourse and 50 m from any spring, well, or borehole | §5.2.2.1 | Should | Application-side setback is 'should'. Stockpile-side waterway-proximity avoidance is 'must' — captured in A1 SOP. Don't bind ourselves to specific application-side distances when the protocol doesn't. | Specific site has clear water-proximity issue requiring formal setback documentation.
X9 | Recommended characterization parameters: WHC, BET surface area, porosity, particle size distribution, VMC, Total Oxygen, bulk carbon bonding state, external surface bonding, CEC | §3.2, §3.3 (Tables 1 & 2 'Recommended') | Recommended | Not required for Option 1 200-yr durability crediting. Running them adds lab cost and PDD documentation overhead with no compliance return. | Pursuing Option 2 (1000-yr) durability — different recommended set applies.
X10 | 1000-year durability quantification (random reflectance R0 with ≥500 maceral-level measurements; reactive vs. residual organic carbon by thermogravimetric analysis) | §5.1.2.2.2 | Required only for Option 2 (1000-yr) | Charm credits under Option 1 (200-yr). Option 2 not in scope. | Strategic decision to pursue Option 2 crediting.
X11 | Combining Durability Options (200-yr + 1000-yr from one facility under unified validation) | §5.1.3 | Optional | Not in scope. Adds temporal + spatial separation overhead and separate verifications for each tier. | Strategic decision to combine durability tiers.
X12 | §9.7.3 mixing process evidence for composter sales: photos/videos of biochar integration into organic mixture (at least once per verification); weighbridge or inventory records from receiving facility | §9.7.3 | Strongly recommended (per Isometric explicit clarification) | Isometric Mar 30, 2026 response: 'Isometric strongly recommends that suppliers provide photo and visual evidence of third-party mixing, but this is not a mandatory requirement…The mandatory evidence requirements remain those set out in sections 8.7.1 and 8.7.2.' Same applies to weighbridge records. Charm has explicit clarification — do not build collection workflow for these. | Isometric retracts the clarification, or strategic decision to provide as defense-in-depth.
X13 | High-resolution maps or GIS layers / parcel IDs delineating direct-to-soil application area (strict §9.5.2 reading) | §9.5.2 | Modified by Isometric agreement | Apr 27 closeout doc, Tom-confirmed May 5: 'Charm will continue to provide a street address and/or GPS coordinates for each spreading location, consistent with the evidence accepted in prior reporting periods.' Address/GPS is the agreed boundary documentation — no maps or GIS shapefiles required. | Isometric retracts the agreement, or VVB raises issue at verification (then escalate via items log).
X14 | Indoor storage of stockpiled biochar (recommended in §7.3) | §7.3 | Recommended — explicitly waived by Isometric | Mar 30, 2026 response §2.2: 'The module recommends indoor storage under stockpiling conditions but does not require it. We agree that Charm's current practice, storage in tied-off supersacks in an outdoor staging area, satisfies the module's weatherproof cover provision. No further action is needed on this point.' | n/a — explicitly closed.

## Open Dependencies
ID | Dependency | Blocker for | Owner | Status
D1 | Brenner application records back-fill: actual application dates and estimated acreage from Brenner grower contact, captured in written attestation | A2 evidence package for existing Brenner inventory | Katie | Open
D2 | Soil Control Labs ISO 17025 accreditation status confirmation for our analytes | A7, P4, C2 (third item) | Steven + Brian | Open
D3 | Application-records DB: named Ops owner for ongoing population and maintenance after MRV builds | A3 handoff | Ops leadership | Open
D4 | Next biochar reporting period dates (start, cutoff, verification) | All target dates in Sheet 1 | Max + Ops | Open