## Findings Register
Brenner Farms Biochar — Review Findings Register
Project: | Brenner Farms biochar deliveries (prj_1JN6XNWDQ1S0BSN7)
Reviewer: | Max Lavine
Responder: | Garrett Lutz
Date raised: | 2026-07-26
Source: | Internal review thread, Slack DM (2026-07-26)
Legend: | CAR = Corrective Action Request (data/calc must be corrected or evidenced) ¦ CL = Clarification Request (explanation / organization)
ID | Type | Delivery / Scope | Reference | Finding (reviewer observation) | Project response (Garrett) | Required action / reviewer assessment | Status | Date closed
CAR-01 | CAR | 1/20 Brenner delivery | Removal rmv_...D393 → Sequestration component cmp_...RXMZ | The mass recorded in the Sequestration component does not correspond to any of the "Dry biochar weight" cells in the ops notes for this delivery. The sequestered mass cannot currently be traced to a source figure in the delivery evidence. | (none yet) | Reconcile the Certify Sequestration mass to a specific "Dry biochar weight" value in the ops notes, or correct the Certify entry. The mass entered must trace to an evidenced figure. | Open
CAR-02 | CAR | 3/11 Brenner delivery | Delivery notes (weight inputs); no scale ticket on file | No scale tickets for this delivery. Gross/tare/net weights are entered as hard-coded inputs (e.g. gross 58,760 lbs) with no shown derivation. If the weight is volumetric, the calculation converting volume to mass is not visible, so the entered weights cannot be substantiated from source. | "No scale tickets for this one, it's all volumetric." "It's tagged in the delivery notes... like where the scale ticket weights usually are." | Show the volumetric-to-mass calculation (volume, density/bulk-density basis, and result) in the delivery notes so each weight is derived rather than hard-coded. A tag in the weight cell is not sufficient to evidence how 58,760 lbs was arrived at. | Open
CL-01 | CL | Brenner delivery folder(s) | "Additional documentation" folder (drive folder 1jcy5rCU...) | An "Additional documentation" folder is present inside the Brenner delivery documentation but its contents are not specific to Brenner deliveries. Its relevance and placement are unclear. | (none yet) | Clarify what this folder is for and whether it belongs with the Brenner delivery package; relocate or remove if not delivery-specific. | Open
CL-02 | CL | All Brenner deliveries | Brenner Farms Delivery Notes.xlsx (master) vs. per-folder delivery notes | Two overlapping sets of delivery notes exist: a truncated set inside the individual delivery folders, and a more detailed master workbook (one tab per delivery, transport broken out). The duplication makes it unclear which is authoritative. | Master workbook "Brenner Farms Delivery Notes.xlsx" is the source of truth (one tab per delivery, transport broken out) and supersedes the per-folder notes; folders are "all jumbled right now." | Resolved in principle: master workbook is authoritative and supersedes the per-folder notes. Action pending: consolidate to a single comprehensive set per delivery and remove/replace the superseded folder notes so there is no competing copy. | Resolved — cleanup pending