## Draft Removals — Open Items
Draft Removals — Open Items Checklist
Source: Certify draft removals (17) cross-checked vs local QA registries + outputs/qa/, 2026-05-11
Site Emissions excluded per scope. Mark column A ✓ as items close.
✓ | Priority | Batch | Removal ID | Date | Net (tCO₂e) | Category | Finding | Next action | Owner | Counts
| P1 FAIL | 2-188 | rmv_1KQB5MBJB1S0N8MR | 03 Apr 2026 | 25.49 | FAIL — BCU over-applied | BCU = 5.582 t vs sister-pattern ~1.129 t (Net inflated ~17%); A4 cert filename also differs from A3 sisters. | Sign off on v2 checklist → send to Garrett to either replace BCU with ~1.129 t or document allocation. | Max → Garrett | Open FAILs (P1) | 4
| P1 FAIL | 2-183 | rmv_1KQ7XZ14K1S09ANA | 02 Apr 2026 | 30.88 | FAIL — BCU missing | Adjustments / BCU Transport = 0; sister 2-182 had 1.594 t. Transport process 1.678 t left un-credited. | Local checklist exists but never sent. Review then send to Garrett. | Max → Garrett | Material flags (P2) | 2
| P1 FAIL | 2-182 | rmv_1KQ7XY3Q81S0T52T | 02 Apr 2026 | 30.39 | FAIL — Stale rail embodied EF | Rail Embodied EF = 0.0000352 (2025) vs current 0.0000311 MTCO₂e/mi. Immaterial here but shared across all rail. | Awaiting Garrett since 04-28. Ping if no response. | Garrett | Never QA'd (P3) | 3
| P1 FAIL | K-002 | rmv_1KQ0QGNBV1S0B315 | 21 Apr 2026 | 9.24 | FAIL — likely already resolved | Outdated 2025 Non-Tanker Truck Embodied EF (0.0401 → 0.1198). Certify Net 9.24 vs QA 9.378 → Δ 0.14 t matches the FAIL fix; Garrett may have already corrected. | Confirm in Garrett's thread, then close. | Garrett (verify) | Hygiene-only (P4) | 9
| P2 Material | 2-192 | rmv_1KQJKRFN61S0EQRP | 11 Apr 2026 | 36.93 | Material flag — C outlier likely resolved | QA flagged 53.1% C (+2.247 SD, lab cert flagged '#'). Registry Net 40.04 vs Certify 36.93 → Δ −3.11 t (−7.8%) suggests C value was re-pulled. | Confirm with Garrett what changed, then close. | Garrett (verify) | Pending Max input (P5) | 2
| P2 Material | 2-184 | rmv_1KQ7Y019T1S0X0WC | 02 Apr 2026 | 31.34 | Material flags — never sent | 8 FLAGs: COBB row 61 F61 = 21,457 kg vs Ops Notes 21,845 kg (Δ 387.91 kg / 1.78%); offload_4 deficit 12,031 kg (15.4%) pending 2-185 closeout; trailer OCR confirmation needed. | Local checklist exists but never sent. Review then send to Garrett. | Max → Garrett | Total open items | 20
| P3 No QA | 2-180 | rmv_1KQJFNB7E1S0X8B9 | 01 Apr 2026 | 30.77 | Not QA'd | AECN, 19.629 t injected, 47.20% C. No local checklist anywhere. | Run AECN batch-qa skill. | Claude | Draft removals on Certify | 17
| P3 No QA | 2-181 | rmv_1KQJFP6Q41S0778B | 01 Apr 2026 | 23.23 | Not QA'd | AECN, 19.665 t injected, 36.60% C. No local checklist anywhere. | Run AECN batch-qa skill. | Claude
| P3 No QA | K-001 | rmv_1KQT5AWP41S0D5MG | 01 Apr 2026 | 8.8 | Not QA'd | Kerry, 4.543 t injected, 54.28% C. No local checklist anywhere. | Run Kerry batch-qa-kerry skill. | Claude
| P4 Hygiene | 2-201 | rmv_1KQT77FNY1S0J259 | 23 Apr 2026 | 30.52 | Flag-only — awaiting Garrett | 3 flags: empty Testing subfolder, COBB row 88 placeholder values, recurring rail filename hygiene. | Awaiting Garrett response. | Garrett
| P4 Hygiene | 2-204 | rmv_1KQYYB3JV1S0RD0R | 29 Apr 2026 | 6.84 | Flag-only — awaiting Garrett | 7 flags: cross-RP railcar reconciliation (FC11 moves to May RP last-reported batch); same hygiene set. | Awaiting Garrett response; track railcar-level reconciliation into May RP. | Garrett
| P4 Hygiene | 2-191 | rmv_1KQJKQCX31S07CNZ | 11 Apr 2026 | 25.7 | Flag-only — awaiting Garrett | 1 flag: rail-batch hygiene (filenames, BCU cert pattern). | Awaiting Garrett response. | Garrett
| P4 Hygiene | 2-190 | rmv_1KQJKPBTM1S0KPEX | 10 Apr 2026 | 26.27 | Flag-only — awaiting Garrett | 1 flag: same rail hygiene set. | Awaiting Garrett response. | Garrett
| P4 Hygiene | 2-189 | rmv_1KQB5KCQG1S0JYZ2 | 03 Apr 2026 | 29.63 | Flag-only — awaiting Garrett | 2 flags: COBB row 66 stale origin_quantity_kg; rail filename hygiene. Also pending Garrett confirmation: which truck physically last from TIMX201060 (2-188 vs 2-189). | Awaiting Garrett response. | Garrett
| P4 Hygiene | 2-187 | rmv_1KQB5JF7Q1S0GN9C | 03 Apr 2026 | 29.47 | Flag-only — awaiting Garrett | 2 flags: COBB row 64 stale + pH typo (33 vs 3.3); rail filename hygiene. | Awaiting Garrett response. | Garrett
| P4 Hygiene | 2-186 | rmv_1KQB5HD031S0REDR | 03 Apr 2026 | 30.26 | Flag-only — awaiting Garrett | 2 flags: COBB origin_quantity_kg stale (pre-correction); rail filename hygiene. | Awaiting Garrett response. | Garrett
| P4 Hygiene | 2-185 | rmv_1KQ7Y0Y4S1S023MT | 02 Apr 2026 | 17.08 | Flag-only — awaiting Garrett | 2 flags: COBB row 61 (sister 2-184) ~388 kg divergence; rail filename hygiene. | Awaiting Garrett response. | Garrett
| P4 Hygiene | 2-174 | (historical) | — |  | Flag-only — awaiting Garrett (stale) | 1 FAIL (tractor # mismatch, 2.3) + 1 flag (filename). Awaiting Garrett since 2026-04-06 — likely cold. | Decide: ping Garrett or close as stale. | Max
| P5 Max input | 2-169 | (not in draft list) | — |  | Pending Max input | Row 41 COBB date mismatch — Garrett claims Column K; QA checked Column H. Needs Max to verify Column K. | Open COBB, verify Column K shows 3/21, flip Row 41 to PASS. | Max
| P5 Max input | 2-160 | (not in draft list) | — |  | Pending Max input | Checklist xlsx missing from workspace. Garrett confirmed EFs; rows 12 + 86 still open. | Locate / provide the 2-160 checklist xlsx. | Max