## Onboarding Checklist
New Feedstock / Oil Source Onboarding Checklist
Owner: | Max Lavine, Carbon Protocol & Verification Lead |  |  |  | Worked Example: | Kerry (totes, flatbed — not yet verified as of March 2026)
Applies to: | Any new bio-oil feedstock, oil source, or pyrolysis technology |  |  |  | Governing Protocol: | Isometric Standard v2.0 + Bio-oil Geological Storage + feedstock/sub-modules
Project: | Charm Industrial — Bio-oil Geological Storage (Basco 6, Vaulted Deep) |  |  |  | Site(s) affected: | Basco 6 (Permeable Reservoirs), Vaulted Deep (Salt Caverns)
Last updated: | 2026-04-23 |  |  |  | Status legend: | Not Started / In Progress / Complete / Blocked / N/A
ID | Phase | Task | Requirement Detail | Protocol / PDD Reference | Owner | Trigger / Timing | Generic Status | Kerry Status | Evidence / Notes
1. Feedstock Eligibility & Sourcing
1 | 1. Feedstock Eligibility & Sourcing | Assign eligibility category (SC1–SC7) | Classify the feedstock under one of SC1–SC7. Gather the listed evidence (e.g., SFI/FSC/PEFC chain-of-custody, third-party low-risk determination) and demonstrate any sub-criteria (SC1.2 stable/increasing forest stocks, SC1.3 no primary forest). | Biomass Feedstock Accounting v1.3 §2.1 Table 1; Table 6 (certifications) | MRV / Feedstock | Before PDD revision | Not Started | In Progress | Kerry expected SC1 (wood-processing residue), analog to AECN. Confirm residue class and certification pathway with supplier.
2 | 1. Feedstock Eligibility & Sourcing | Prohibited-feedstock screen | Confirm feedstock is not PF1 or PF2. For wood-processing residues, demonstrate non-marketable status or bioenergy/landscape/mulch-only market for the prior 2 years. | Biomass Feedstock Accounting v1.3 §4.1 Table 3 | MRV / Feedstock | Before PDD revision | Not Started | Not Started
3 | 1. Feedstock Eligibility & Sourcing | Document counterfactual fate | 5-year historical evidence from supplier (purchase records, production records, supplier affidavit). AECN precedent treated mill sawdust as 'no counterfactual use' → replacement emissions = 0. | Biomass Feedstock Accounting v1.3 §3.1 | MRV / Feedstock | Before PDD revision | Not Started | Not Started
4 | 1. Feedstock Eligibility & Sourcing | Select counterfactual criterion (CC1/CC2/CC3) | Pick CC1 (decay/dispersion), CC2 (wildfire program), or CC3 (quantified). If CC3, run the counterfactual-storage quantification (Equations 1–2), including 50-year option for GWP-weighted near-term releases. | Biomass Feedstock Accounting v1.3 §3.2 Table 2; §3.3 Eq. 1–2 | MRV / Feedstock | Before PDD revision | Not Started | Not Started
5 | 1. Feedstock Eligibility & Sourcing | Market-leakage assessment | ML1 quantification or qualifying criterion (ML2–ML7). Industry Residues in Appendix 5 are pre-screened low-risk (ML5.1/SC5.1). | Biomass Feedstock Accounting v1.3 §4.2; Appendix 5 | MRV / Feedstock | Before PDD revision | Not Started | Not Started
6 | 1. Feedstock Eligibility & Sourcing | Draft new Feedstock Appendix to PDD | Stand-alone appendix for the new source (parallel to Apps 1 AECN, 2 MacArthur Gulch, 3 Arkansas Mtn, 4 Arroyo Chico): feedstock description, sustainability evidence, counterfactual fate, leakage assessment, baseline-emission treatment. | PDD Apps 1–4 pattern | MRV / Feedstock | With PDD revision | Not Started | Not Started | Kerry appendix to be drafted as Appendix 5 (or next available).
2. Storage / Injectate Compatibility
7 | 2. Storage / Injectate Compatibility | Extend standard test panel with major anions + cations | On the first production batch representing a feedstock or pyrolysis-process change, extend the standard injectant panel (pH, density, viscosity, TAN, C content) to include major anions and cations. | PDD Appendix 7 §3.1.1 (p.138); Bio-oil Storage in Permeable Reservoirs §3.1.1 (optional major/minor ions, geochemical fingerprint) | Ops / Lab (SGS) | Before first injection | Not Started | Not Started | Explicitly required by storage appendix because Kerry = new feedstock and new pyrolysis.
8 | 2. Storage / Injectate Compatibility | Baseline density measurement (ASTM D4052-22 / D7042-21a) | Measure density prior to first injection; confirm it exceeds formation-fluid density (~1.01 g/cm³) so oil sinks. | Bio-oil Storage in Permeable Reservoirs §3.1.1, §3.2 | Ops / Lab | Before first injection | Not Started | Not Started | Required for every new oil; also repeats per-batch.
9 | 2. Storage / Injectate Compatibility | Viscosity, TAN, pH, C content baseline | Full standard panel measured for the new stream and compared to existing AECN/Charm ranges. Flag any parameter outside established envelopes. | Bio-oil Storage in Permeable Reservoirs §3.1.1 | Ops / Lab | Before first injection | Not Started | Not Started
10 | 2. Storage / Injectate Compatibility | Material compatibility / corrosion screening | Run NREL short-term alloy exposure screen for well materials. Extend Charm's ongoing material-compatibility work to the new oil. | Bio-oil Storage in Permeable Reservoirs §3.1.2 (NREL footnote 14); PDD p.136 | Injection Eng. | Before first injection | Not Started | Not Started
11 | 2. Storage / Injectate Compatibility | Core reactivity / polymerization test | Lab-scale reactivity of oil with reservoir lithology, including polymerization/solidification rate. Calcium reactivity is Charm's primary candidate-selection screen. | Bio-oil Storage in Permeable Reservoirs §2.2; PDD p.136 | Injection Eng. | Before first injection | Not Started | Not Started
12 | 2. Storage / Injectate Compatibility | Site-characterization review triggered by injectant change | §2.2 requires site characterization to be reviewed when injectant characteristics change materially. Reconfirm reservoir lithology, porosity/permeability, confining-layer integrity, formation-fluid chemistry, dissolved gas, δ18O/δD, hydrocarbon background remain valid. | Bio-oil Storage in Permeable Reservoirs §2.2 | Subsurface / MRV | Before first injection | Not Started | Not Started
13 | 2. Storage / Injectate Compatibility | Salt-cavern-specific re-measurement (if injecting at Vaulted) | Salt Caverns §3.1.1 explicitly requires repeating measurements every time there is a material upstream process change like a new biomass feedstock; blended feedstocks require per-emplacement sampling. | Biomass or Bio-oil Storage in Salt Caverns §3.1.1; §2.3 well materials | Ops / MRV | If Vaulted is ever used | Not Started | N/A | Basco 6 is current site; mark N/A unless Vaulted returns to service.
14 | 2. Storage / Injectate Compatibility | Non-hazardous determination | Independent determination that the final bio-oil product is non-hazardous. Required precondition for injection eligibility; critical for KDHE Class V permit at Vaulted. | Val Report 27 §2.5.3 | MRV / EHS | Before first injection | Not Started | Not Started
15 | 2. Storage / Injectate Compatibility | UIC permit review (LDENR / KDHE) | Confirm current UIC permit language covers the new injectate. If materially different chemistry, file a permit amendment. MASIP at Basco = 455 psi. | PDD App 7; LDENR (Basco) / KDHE (Vaulted) permit files | Regulatory / Ops | Before first injection | Not Started | Not Started
3. Pyrolysis / Production Characterization
16 | 3. Pyrolysis / Production Characterization | Define new pyrolysis methodology memo | Stand-alone memo documenting process description, I/O inventory, boundary, allocation, and CI derivation for the new producer. Required as gate to first submission. | Val Report 27 precedent; KB §10A item 6d | MRV | Before first submission | Not Started | In Progress | Kerry memo is under development; Certify submissions must NOT proceed until approved.
17 | 3. Pyrolysis / Production Characterization | Full inputs/outputs inventory | Biomass feed, water, diesel (handling + transport), electricity, propane, embodied equipment, bio-oil, tailgas, biochar, unders, wastes. | Val Report 27 §3.2 Table 3 | MRV | With methodology memo | Not Started | Not Started
18 | 3. Pyrolysis / Production Characterization | Process EF + Embodied EF (CI) for new producer | Document process and embodied emission factors (kgCO₂e/kg). Reference values: AECN = 0.10402 process, 0.0212 embodied. | Charm Isometric KB §6; Certify Deep Dive | MRV | With methodology memo | Not Started | Not Started
19 | 3. Pyrolysis / Production Characterization | Stack-emissions LCA file | LCA-with-stack-emissions file attached to the Sources tab for every removal using the new oil (mandatory under QA checklist §6a). | Charm Isometric KB §10A item 6a | MRV | With methodology memo | Not Started | Not Started
20 | 3. Pyrolysis / Production Characterization | Co-product allocation procedure | Select P1–P4 (mass, energy, economic, substitution). If biochar is credited alongside bio-oil, Procedure 4 carbon mass balance is required. | GHG Accounting v1.0 §6 + App D §13.4; PDD p.3389 | MRV | With methodology memo | Not Started | Not Started
21 | 3. Pyrolysis / Production Characterization | Energy-use characterization | Metered electricity, propane, diesel, waste-heat utilization for the production facility. Apply intensive-facility test at 200 GWh/yr. | Energy Use Accounting v1.3 | MRV | With methodology memo | Not Started | Not Started
22 | 3. Pyrolysis / Production Characterization | Biomass-transport accounting | Origin, distance, mode, and allocation method for biomass feeding the new producer. | Transportation Emissions Accounting v1.1; PDD p.1322 allocation approach | MRV | With methodology memo | Not Started | Not Started
23 | 3. Pyrolysis / Production Characterization | Uncertainty & sensitivity analysis update | Propagate new component uncertainties into the overall removal variance per Standard §3.7.3. Add per-datapoint uncertainty to Certify per KB §7a. | Isometric Standard v2.0 §3.7.3; KB §7a | MRV | With methodology memo | Not Started | Not Started
4. PDD Revision & Notifications
24 | 4. PDD Revision & Notifications | Notify Isometric of operational change | Formal notification that a new oil source / pyrolysis tech is being added. §3.3 says eligibility must be assessed at next verification following notification. | Isometric Standard v2.0 §3.3; PDD p.368 acknowledgment | MRV | Before first injection | Not Started | Not Started
25 | 4. PDD Revision & Notifications | Assess material-change scope | Document whether change meets §2.4.3 materiality test (affects how validations/verifications are conducted or their outcomes). A new feedstock/producer is material at the Project-scope level. | Isometric Standard v2.0 §2.4.3 | MRV | Before PDD revision | Not Started | Not Started
26 | 4. PDD Revision & Notifications | Revise PDD (narrative sections) | Update §3 Project Description, system boundary, SSRs, monitoring plan, uncertainty, and §3.iv.b Injectate Characterization to include the new stream. | Isometric Standard v2.0 §3.2; PDD §3.iv.b | MRV | Before first claim | Not Started | Not Started
27 | 4. PDD Revision & Notifications | Updated GHG Statement for new oil | Updated GHG Statement plus uncertainty analysis plus bio-oil sampling & analysis results must be in-hand prior to first verification of removals involving the new oil. | Val Report 27 §4.2 Table 5 | MRV / Verifier | Before first claim | Not Started | Not Started
28 | 4. PDD Revision & Notifications | VVB re-scoping & targeted validation | Scope-limited validation of the new producer/feedstock (precedent: Val Report 27 covered MiniForge only, without re-validating AECN). Activities: facility walkthrough, process I/O review, compliance checklist. | Val Report 27 §3.1 (scope); Table 2 activities; Isometric Standard v2.0 §3.3 | MRV / 350Solutions | Before first claim | Not Started | Not Started
29 | 4. PDD Revision & Notifications | Reversal-assessment / buffer review | Confirm whether the new stream alters the reversal risk classification. If yes, buffer-pool allocation is reassessed per §5.6.3. | Isometric Standard v2.0 §5.6.3 | MRV | Before first claim | Not Started | Not Started
5. Certify / dMRV Configuration
30 | 5. Certify / dMRV Configuration | Confirm feedstock record is added & VVB-validated | Feedstock must be added to Certify at the source level and validated by the VVB before removals can be submitted. | Certify schema; VVB validation record | MRV | Before first submission | Not Started | Complete | Done for Kerry — feedstock added to Certify and VVB-validated (per Max).
31 | 5. Certify / dMRV Configuration | Build Origin datapoint | Create 'Origin Bio-Oil Mass — [Supplier]' datapoint mirroring the AECN pattern. | Certify Deep Dive; KB §3 naming conventions | MRV / Certify | Before first submission | Not Started | Not Started
32 | 5. Certify / dMRV Configuration | Build Pyrolysis components | Create '[Supplier] Pyrolysis Process Emissions' + '[Supplier] Pyrolysis Embodied Emissions' components with CI datapoints (or Production-Period tracking if Charm-produced). | KB §5 Certify evolution; §6 EF table | MRV / Certify | Before first submission | Not Started | Not Started
33 | 5. Certify / dMRV Configuration | Build Transport components | Match transport mode to the oil: Flatbed Truck Process + Embodied for totes; Tanker Truck for AECN-style direct; Railcar for rail. | KB §6; QA checklist §3 (mode-to-oil rule) | MRV / Certify | Before first submission | Not Started | Not Started | Kerry expected on flatbed, same as Charm totes.
34 | 5. Certify / dMRV Configuration | Build Pre-treatment components (if applicable) | LCS (1,505.78 kg/m³ embodied) and/or sparging (1.29% mass deduction for AECN) as Injection activities, only if the new oil receives pre-treatment. | KB §6, §9 Basco 6 Operations | MRV / Certify | Before first submission | Not Started | Not Started
35 | 5. Certify / dMRV Configuration | Match BCUs to diesel / process emissions | Every transport and pre-treatment diesel activity for the new stream needs a matching BCU reduction ≥ the emission on every removal. | KB §5 BCU QA Rule; §6 | MRV / Certify | Before first submission | Not Started | Not Started
36 | 5. Certify / dMRV Configuration | Attach Sources tab files | Three files per pyrolysis source on Sources tab: LCA CI spreadsheet, LCA with stack emissions, supporting GHG data for the production period. | KB §10A item 6a | MRV / Certify | Before first submission | Not Started | Not Started
37 | 5. Certify / dMRV Configuration | Load per-datapoint uncertainty | Mass and CI uncertainty entered per datapoint per KB §7a three-layer verification (completeness, correct datapoint mapping, propagation). | KB §7a; MRV Uncertainty+ Evidence Cheat Sheet.xlsx | MRV / Certify | Before first submission | Not Started | Not Started
6. Transportation
38 | 6. Transportation | Document origin, route, distance | Lock supplier origin and injection destination; document route and distance. Needed for distance-based EF application. | Transportation Emissions Accounting v1.1 §3.3 | Logistics / MRV | Before first shipment | Not Started | In Progress | Kerry origin still TBD per Certify Deep Dive.
39 | 6. Transportation | Apply mode-appropriate EFs | Flatbed (Kerry/Charm totes): 0.14 kg/(t·mi) process, 0.0401 kgCO₂e/km embodied. Confirm EFs are <5 years old. | Transportation Emissions Accounting v1.1 §3.4; KB §6 | MRV | Before first submission | Not Started | Not Started
40 | 6. Transportation | BOL / routing evidence protocol | Truck BOL per shipment; rail = 3 BOLs per railcar. Origin/destination must match the PDD and the Certify transport mode. | Transportation Emissions Accounting v1.1 App 1; KB QA §3 | Ops / MRV | Every shipment | Not Started | Not Started
7. Site Operations & Chain-of-Custody
41 | 7. Site Operations & Chain-of-Custody | Define pre-treatment plan | Decide whether new oil is sparged, LCS-treated, or injected raw. If different from current streams, update PDD §3.iv.b and operating procedures at El Dorado / Basco. | PDD §3.iv.b; KB §6 pre-treatment | Ops | Before first injection | Not Started | Not Started | Kerry pre-treatment approach still undefined.
42 | 7. Site Operations & Chain-of-Custody | QC sampling at every transfer | Jar sample at each transfer event → SGS full characterization (density, composition, moisture, viscosity, CHN, TAN, acid number). | KB §9 QC Sampling | Ops / Lab | Every transfer | Not Started | Not Started
43 | 7. Site Operations & Chain-of-Custody | Chain-of-custody artifacts per batch | Scale tickets (full + empty, matching tractor/trailer), BOL, COBB tracker row, Ops Notes, CHN PDF — every batch, for the new oil too. | KB Gate 1 mandatory reads (scale tickets, BOL, lab); COBB tracker | Ops | Every batch | Not Started | Not Started
44 | 7. Site Operations & Chain-of-Custody | Inventory / lot allocation | Conservative upstream-emissions allocation (+25% loss buffer) against oldest BOL. Extend the convention to new source once on-stream. | PDD p.3403; KB §9 Inventory Management | MRV / Ops | Ongoing | Not Started | Not Started
45 | 7. Site Operations & Chain-of-Custody | Alarms / containment integrity | Gas detectors w/ injection shut-off on each well; 6-month corrosion monitoring or NREL short-term alloy exposure program. | Bio-oil Storage in Permeable Reservoirs §3.1.2 | Injection Eng. | Ongoing | Not Started | Not Started
46 | 7. Site Operations & Chain-of-Custody | Annual regulatory affirmation | Regulatory-compliance affirmation from each third-party participant involved in the new stream. | PDD §6a | MRV | Annual | Not Started | Not Started
47 | 7. Site Operations & Chain-of-Custody | Reversal / alarm reporting protocol | Report reversal events / alarms to VVB and Isometric within 1–3 business days. | Isometric Standard v2.0 §5.6.1; PDD §5.c.i.2 | Ops / MRV | Event-driven | Not Started | Not Started

## Reference Index
Protocol / PDD Reference Index
Document | Relevant Sections (with page where known)
Isometric Standard v2.0 | §2.4.3 Protocol-update materiality; §3.2 Documentation; §3.3 Eligibility & change notification; §3.4 Crediting Period; §3.7.3 Uncertainty propagation; §5.6.1 Reversal reporting (1–3 business days); §5.6.3 Reversal assessment / buffer
Bio-oil Geological Storage Protocol v1.1 | Core equation: CO₂eRemoval = CO₂eStored − CO₂eCounterfactual − CO₂eEmissions
Bio-oil Storage in Permeable Reservoirs v1.1 (Basco 6) | §2.2 Site characterization (review on injectant-characteristic change; lab core reactivity / polymerization); §3.1.1 Injection and Injectant Operation & Monitoring (standard panel + optional major/minor ions, ASTM D4052/D7042 density); §3.1.2 Corrosion monitoring + NREL short-term alloy exposure (footnote 14); §3.2 Post-Injection Monitoring (density vs formation-fluid)
Biomass or Bio-oil Storage in Salt Caverns v1.1 (Vaulted) | §3.1.1 Re-measurement on every material upstream process change; blended-feedstock per-emplacement sampling; §2.3 well-material compatibility
Biomass Feedstock Accounting v1.3 | §2.1 Table 1 SC1–SC7; Table 6 listed certifications; §3.1 Counterfactual fate evidence; §3.2 Table 2 CC1–CC3; §3.3 Eq. 1–2 counterfactual storage; §4.1 Table 3 prohibited feedstocks; §4.2 ML1–ML7 market leakage; Appendix 5 Industry Residues
Energy Use Accounting v1.3 | CO₂eEnergy = CO₂eElectricity + CO₂eFuel; intensive vs non-intensive facility threshold 200 GWh/yr; EC1–EC6 EAC criteria
Transportation Emissions Accounting v1.1 | §3.3 Distance-based method; §3.4 Acceptable EFs (5-yr max age, mode-specific); Appendix 1 mode-specific evidence; BCU EC1–EC5 criteria and offset rule
GHG Accounting v1.0 | §6 + Appendix D Allocation Procedures P1–P4; §13.4 Procedure 4 carbon mass balance for credited co-products
PDD (22_2025-02-20_pdd.pdf) | §3 Project description; §3.iv.b Injectate Characterization; §6a Annual regulatory affirmation; Appendix 1 AECN feedstock; App 2 MacArthur Gulch; App 3 Arkansas Mtn; App 4 Arroyo Chico; Appendix 7 §3.1.1 (p.138) anion/cation extension; p.136 material-compatibility + calcium reactivity; p.1322 biomass-transport allocation; p.3389 three-product co-product allocation; p.3403 +25% loss buffer / oldest-BOL allocation; p.368 change notification acknowledgment; §5.c.i.2 reversal reporting timing
Val Report 27 (2024-10-18 Charm validation) | §2.5.3 Non-hazardous determination requirement; §2.5.7 Updated uncertainty/sensitivity; §3.1 Scope-limited validation precedent (MiniForge only); §3.2 Table 3 pyrolysis I/O inventory; §4.2 Table 5 precondition to first verification
Charm Isometric Knowledge Base | §3 Oil Types & Feedstock Streams (Kerry status); §5 Certify platform evolution; §6 Emission factors; §7a Per-component uncertainty verification; §9 Mass accounting, sparging, QC sampling, inventory; §10A Injection batch QA checklist (item 6a Sources-tab files, item 6d Kerry methodology memo gate)