## Active Batches
Batch ID | Status | Date Sent | Slack Channel | Certify URL | Fails | Flags | Fail Details | Flag Details
2-174 | Awaiting Garrett | 2026-04-06 | D08KEFVRJDP | https://registry.isometric.com/removals/rmv_1KMR8G8VC1S0G1ZG | 1 | 1 | Row 18 (§2.3): Tractor number mismatch resolved — either corrected in Certify or documented explanation provided → Scale ticket source documents | Row 79 (§9.9): Screenshot filename renamed to something descriptive → Sources tab — AECN Production Process Emissions

## Pending Max Input
Batch ID | Notes / Open Items
2-169 | 6 of 7 findings resolved (2026-04-01). Row 41 COBB date mismatch: Garrett claims Ops Notes follows Column K, QA checked Column H. Max needs to verify Column K shows 3/21 for 2-169. Once confirmed, Row 41 flips to PASS and thread can be closed. Checklist: batch-qa-checklists/Batch_2-169_QA_Checklist.xlsx
2-160 | Garrett updated EFs (2026-04-01): Vehicle Embodied 0.1476 kgCO2e/km confirmed in Certify; AECN Process EF stated as 0.10402 (Certify UI truncates, cannot verify exactly). Still open: (1) Row 12 scale tickets not confirmed in Drive; (2) Row 86 net removal needs re-check; (3) batch-qa-checklists/Batch_2-160_QA_Checklist.xlsx does not exist in workspace — Max needs to provide this file before QA can be updated or closed.